## Horizon Plan
Sample Horizon Plan
by David A. Penny | https://modsoftman.com/hp-sheet
Summary:
Development Plan Start Date | 2022-04-04
Calendar Work Days Done | 121
As at (last updated date): | 2022-10-03
Calendar Work Days Remaining | 36
Target End of Development | 2022-11-24
Calendar Work Days Stabilization | 78.5
Calendar Work Days Validation | 20
Target Internal Release Date | 2023-04-17
ECDs Logged to date | 1109.4783
Planned Effective Coders - N estimated | 10.1333
Measured Effective Coders - N actual | 10.3493
Remaining Capacity ECDs | 364.8
A-List Requirement ECDs | 284.75
Delta ECDs | 80.05
Delta Percent | 78.06%
Developer Capacity:
Developer | Availability | Vacation | Work Factor | ECDs Available | ECDs Required | Delta | %Load
Team A |  |  |  | 55.8 | 2.5 | 53.3 | 4.48%
Team Lead 1 | 100% | 0 | 0.25 | 9
Dev 2 | 100% | 0 | 0.4 | 14.4
Dev 3 | 100% | 0 | 0.4 | 14.4
Dev 4 | 100% | 0 | 0.4 | 14.4
Intern 5 | 100% | 0 | 0.1 | 3.6
Team B |  |  |  | 27 | 20 | 7 | 74.07%
Teram Lead 6 | 100% | 0 | 0.25 | 9
Dev 7 | 100% | 0 | 0.3 | 10.8
Dev 8 | 100% | 0 | 0.1 | 3.6
Dev 9 | 100% | 3 | 0.35 | 0
Intern 10 | 100% | 0 | 0.1 | 3.6
Team C |  |  |  | 59.4 | 65 | -5.6 | 109.4%
Team Lead 11 | 100% | 0 | 0.2 | 7.2
Dev 12 | 100% | 0 | 0.45 | 16.2
Dev 13 | 100% | 0 | 0.45 | 16.2
Dev 14 | 100% | 0 | 0.35 | 12.6
Intern 15 | 100% | 0 | 0.2 | 7.2
Team D |  |  |  | 45 | 0.25 | 44.75 | 0.5556%
Team Lead 16 | 100% | 0 | 0.25 | 9
Dev 17 | 100% | 0 | 0.45 | 16.2
Dev 18 | 100% | 0 | 0.45 | 16.2
Intern 19 | 100% | 0 | 0.1 | 3.6
Team E |  |  |  | 95.4 | 87 | 8.4 | 91.19%
Team Lead 20 | 100% | 0 | 0.25 | 9
Dev 21 | 100% | 0 | 0.47 | 16.92
Dev 22 | 100% | 0 | 0.53 | 19.08
Dev 23 | 100% | 0 | 0.45 | 16.2
Dev 24 | 100% | 0 | 0.6 | 21.6
Dev 25 | 100% | 0 | 0.35 | 12.6
Team F |  |  |  | 66 | 110 | -44 | 166.7%
Team Lead 26 | 100% | 0 | 1.1 | 39.6
Dev 27 | 100% | 3 | 0.8 | 26.4
Team G |  |  |  | 16.2 | 0 | 16.2 | 0%
Dev 28 | 100% | 0 | 0.45 | 16.2
Dev 29 | 50% | 0 | 0.35 | 6.3
Dev 30 | 50% | 0 | 0.55 | 9.9
Unassigned | [5 empty] | 0
TOTAL | 96.67% | 6 | 11 | 364.8 | 284.75 | 80.05 | 78.06%
Devs |  |  | 30
Average Work Factor |  |  | 0.36667
Burn Rate, ECDs/Week |  |  | 55
Customer Service Bucket | CS | 216.7858 | 15.55%
Tech Debt Bucket | TD | 172.94 | 12.4%
Product Management Initiatives | PM | 835.5017 | 59.93%
Business Basics | BB | 169.0008 | 12.12%
A-List Issues:
JIRA Issue | Summary | Category | Dev Team Assigned | Status | ECDs Remaining | ECDs To-Date
JIRA-0013 | Short Description of JIRA-0013 | CS | Team D | Ready for Verification | 0 | 23.0625
JIRA-0022 | Short Description of JIRA-0022 | CS | Team C | In Progress | 1 | 65.63
JIRA-0012 | Short Description of JIRA-0012 | CS | Team E | Ready for Verification | 0 | 35.65
JIRA-0027 | Short Description of JIRA-0027 | CS | Team A | Ready for Demo | 0 | 21.8125
JIRA-0028 | Short Description of JIRA-0028 | CS | Team B | Done | 0 | 1.75
JIRA-0010 | Short Description of JIRA-0010 | CS | Team B | Not Yet Started | 20 | 0
JIRA-0002 | Short Description of JIRA-0002 | CS | Team D | In Progress | 0.25 | 20.0708
JIRA-0016 | Short Description of JIRA-0016 | CS | Team A | Done | 0 | 27.56
JIRA-0003 | Short Description of JIRA-0003 | PM | Team A | In Progress | 2.5 | 193.25
JIRA-0001 | Short Description of JIRA-0001 | PM | Team F | Ready for Verification | 0 | 8.7
JIRA-0006 | Short Description of JIRA-0006 | PM | Team F | In Progress | 110 | 177
JIRA-0007 | Short Description of JIRA-0007 | PM | Team A | Done | 0 | 2.5
JIRA-0019 | Short Description of JIRA-0019 | PM | Team D | Ready for Verification | 0 | 24.8125
JIRA-0017 | Short Description of JIRA-0017 | PM | Team D | Ready for Verification | 0 | 19.8125
JIRA-0011 | Short Description of JIRA-0011 | PM | Team C | In Progress | 50 | 95.81
JIRA-0005 | Short Description of JIRA-0005 | PM | Team B | Done | 0 | 4.25
JIRA-0024 | Short Description of JIRA-0024 | PM | Team D | Done | 0 | 136.1167
JIRA-0030 | Short Description of JIRA-0030 | PM | Team C | Ready for Verification | 0 | 10.75
JIRA-0023 | Short Description of JIRA-0023 | TD | Team E | Ready for Verification | 0 | 0.25
JIRA-0021 | Short Description of JIRA-0021 | TD | Team C | Done | 0 | 13
JIRA-0009 | Short Description of JIRA-0009 | TD | Team E | In Progress | 45 | 66.19
JIRA-0020 | Short Description of JIRA-0020 | TD | Team D | Done | 0 | 10.9375
JIRA-0025 | Short Description of JIRA-0025 | TD | Team E | Done | 0 | 1.8125
JIRA-0029 | Short Description of JIRA-0029 | TD | Team C | In Progress | 14 | 21.75
JIRA-0015 | Short Description of JIRA-0015 | BB | Team A | Ready for Verification | 0 | 21.125
JIRA-0014 | Short Description of JIRA-0014 | BB | Team E | In Progress | 42 | 51.63
JIRA-0026 | Short Description of JIRA-0026 | BB | Team G | Ready for Verification | 0 | 18.4
JIRA-0008 | Short Description of JIRA-0008 | BB | Team G | Done | 0 | 10.125
JIRA-0018 | Short Description of JIRA-0018 | BB | Team G | Done | 0 | 25.7208
A-List Sub-totals |  |  |  |  | 284.75 | 1109.4783
B-List Issues:
JIRA Issue | Summary | Category | Dev Team Assigned | Status | ECDs Remaining | ECDs To-Date
JIRA-0050 | Short Description of JIRA-0050 | PM | Team E | Prioritized | 93 | 0
JIRA-0052 | Short Description of JIRA-0052 | PM | Team B | Prioritized | 25 | 0
JIRA-0053 | Short Description of JIRA-0053 | TD | Team E | In Requirement Review | 82 | 0
JIRA-0055 | Short Description of JIRA-0055 | BB | Team A | Prioritized | 22 | 0
B-List Sub-totals |  |  |  |  | 222 | 0

## Graph Data
[7 empty] | exp decay factor: | 0.1
Date | Workdays | A-List Requirement | B-List Requirement | Capacity | Predicted Capacity | ECDs logged to date | Estimated ECDs | Averaged Daily ECDs
2022-04-04 | 1 | 100 | 100 | 939 |  | 0 | 10.1 | 0
2022-04-05 | 2 | 100 | 100 | 931 |  | 0 | 10.1 | 0
2022-04-06 | 3 | 100 | 100 | 922.4 |  | 0 | 10.1 | 0
2022-04-07 | 4 | 100 | 100 | 915.4022 |  | 9.3875 | 10.1 | 0.93875
2022-04-08 | 5 | 100 | 100 | 908.4144 |  | 18.775 | 10.1 | 1.7836
2022-04-11 | 6 | 100 | 100 | 901.4266 |  | 28.1625 | 10.1 | 2.544
2022-04-12 | 7 | 100 | 100 | 894.4388 |  | 37.55 | 10.1 | 3.2284
2022-04-13 | 8 | 100 | 100 | 887.451 |  | 46.9375 | 10.1 | 3.8443
2022-04-14 | 9 | 100 | 100 | 880.4632 |  | 56.325 | 10.1 | 4.3986
2022-04-19 | 10 | 100 | 100 | 859.4998 |  | 65.7125 | 10.1 | 4.8975
2022-04-20 | 11 | 100 | 100 | 852.512 |  | 75.1 | 10.1 | 5.3465
2022-04-21 | 12 | 100 | 100 | 845.5242 |  | 84.4875 | 10.1 | 5.7506
2022-04-22 | 13 | 346 | 130 | 969 |  | 93.875 | 10.1 | 6.1143
2022-04-25 | 14 | 346 | 130 | 959.375 |  | 98.6953 | 10.1 | 5.9849
2022-04-26 | 15 | 346 | 130 | 949.75 |  | 103.5156 | 10.1 | 5.8684
2022-04-27 | 16 | 346 | 130 | 940.125 |  | 108.3359 | 10.1 | 5.7636
2022-04-28 | 17 | 346 | 130 | 930.5 |  | 113.1562 | 10.1 | 5.6693
2022-04-29 | 18 | 346 | 130 | 920.875 |  | 117.9766 | 10.1 | 5.5844
2022-05-02 | 19 | 346 | 130 | 911.25 |  | 122.7969 | 10.1 | 5.508
2022-05-03 | 20 | 463 | 130 | 901.625 |  | 127.6172 | 10.1 | 5.4392
2022-05-04 | 21 | 463 | 140 | 892 |  | 132.4375 | 10.1 | 5.3773
2022-05-05 | 22 | 463 | 140 | 882.7083 |  | 138.5924 | 10.1 | 5.4551
2022-05-06 | 23 | 463 | 140 | 873.4167 |  | 144.7472 | 10.1 | 5.5251
2022-05-09 | 24 | 463 | 140 | 864.125 |  | 150.9021 | 10.1 | 5.588
2022-05-10 | 25 | 500 | 140 | 854.8333 |  | 157.057 | 10.1 | 5.6447
2022-05-11 | 26 | 500 | 140 | 845.5417 |  | 163.2118 | 10.1 | 5.6957
2022-05-12 | 27 | 600 | 140 | 836.25 |  | 169.3667 | 10.1 | 5.7416
2022-05-13 | 28 | 700 | 140 | 826.9583 |  | 175.5216 | 10.1 | 5.783
2022-05-16 | 29 | 761 | 150 | 816 |  | 181.6764 | 10.1 | 5.8202
2022-05-17 | 30 | 756.21 | 150 | 806.5116 |  | 187.8313 | 10.1 | 5.8536
2022-05-18 | 31 | 751.42 | 150 | 797.0233 |  | 193.9862 | 10.1 | 5.8838
2022-05-19 | 32 | 746.63 | 150 | 787.5349 |  | 200.1411 | 10.1 | 5.9109
2022-05-20 | 33 | 741.84 | 150 | 778.0465 |  | 206.2959 | 10.1 | 5.9353
2022-05-24 | 34 | 737.05 | 150 | 768.5581 |  | 212.4508 | 10.1 | 5.9572
2022-05-25 | 35 | 732.26 | 150 | 759.0698 |  | 218.6057 | 10.1 | 5.977
2022-05-26 | 36 | 727.47 | 150 | 749.5814 |  | 224.7605 | 10.1 | 5.9948
2022-05-30 | 37 | 722.68 | 150 | 740.093 |  | 230.9154 | 10.1 | 6.0108
2022-05-31 | 38 | 912 | 170 | 730.6047 |  | 237.0703 | 10.1 | 6.0252
2022-06-01 | 39 | 912 | 170 | 720 |  | 243.2251 | 10.1 | 6.0382
2022-06-02 | 40 | 900 | 170 | 712.9412 |  | 249.38 | 10.1 | 6.0498
2022-06-03 | 41 | 890 | 170 | 705.8824 |  | 265.5277 | 10.1 | 7.0596
2022-06-06 | 42 | 764 | 180 | 873 |  | 281.6754 | 10.1 | 7.9684
2022-06-07 | 43 | 754 | 180 | 864.0918 |  | 297.8231 | 11.8 | 8.7864
2022-06-08 | 44 | 744 | 180 | 855.1837 |  | 313.9708 | 11.8 | 9.5225
2022-06-09 | 45 | 985 | 180 | 846.2755 |  | 330.1185 | 11.8 | 10.185
2022-06-10 | 46 | 985 | 170 | 891 |  | 346.2662 | 11.8 | 10.7813
2022-06-13 | 47 | 975 | 170 | 881.4194 |  | 362.4138 | 11.8 | 11.3179
2022-06-14 | 48 | 965 | 170 | 871.8387 |  | 378.5615 | 11.8 | 11.8009
2022-06-15 | 49 | 955 | 170 | 862.2581 |  | 394.7092 | 11.8 | 12.2356
2022-06-16 | 50 | 945 | 170 | 852.6774 |  | 410.8569 | 11.8 | 12.6268
2022-06-17 | 51 | 1021 | 160 | 870 |  | 427.0046 | 11.8 | 12.9789
2022-06-20 | 52 | 875 | 165 | 860 |  | 443.1523 | 11.8 | 13.2958
2022-06-21 | 53 | 870 | 160 | 850.1149 |  | 459.3 | 11.8 | 13.581
2022-06-22 | 54 | 865 | 160 | 840.2299 |  | 468.3125 | 11.8 | 13.1241
2022-06-23 | 55 | 855 | 160 | 830.3448 |  | 477.325 | 11.8 | 12.7129
2022-06-24 | 56 | 850 | 160 | 820.4598 |  | 486.3375 | 11.8 | 12.3429
2022-06-27 | 57 | 757 | 170 | 967 |  | 495.35 | 11.8 | 12.0099
2022-06-28 | 58 | 750 | 170 | 957.1327 |  | 504.3625 | 11.8 | 11.7101
2022-06-29 | 59 | 743 | 170 | 947.2653 |  | 513.375 | 11.8 | 11.4404
2022-06-30 | 60 | 737 | 170 | 938 |  | 522.3875 | 11.8 | 11.1976
2022-07-05 | 61 | 726 | 170 | 928 |  | 531.4 | 11.8 | 10.9791
2022-07-06 | 62 | 755 | 180 | 928 |  | 545.95 | 11.8 | 11.3362
2022-07-07 | 63 | 747 | 180 | 949.2135 |  | 560.5 | 11.8 | 11.6575
2022-07-08 | 64 | 740 | 180 | 938.427 |  | 566.4143 | 11.8 | 11.0832
2022-07-11 | 65 | 733 | 180 | 927.6404 |  | 572.3286 | 11.8 | 10.5663
2022-07-12 | 66 | 727 | 180 | 916.8539 |  | 578.2429 | 11.8 | 10.1011
2022-07-13 | 67 | 720 | 180 | 906.0674 |  | 584.1571 | 11.8 | 9.6824
2022-07-14 | 68 | 715 | 180 | 895.2809 |  | 590.0714 | 11.8 | 9.3056
2022-07-15 | 69 | 711 | 180 | 882 |  | 595.9857 | 11.8 | 8.9665
2022-07-18 | 70 | 680 | 180 | 871.8621 |  | 601.9 | 11.8 | 8.6613
2022-07-19 | 71 | 668 | 180 | 860 |  | 631.25 | 11.8 | 10.7301
2022-07-20 | 72 | 664 | 180 | 849.5122 |  | 660.6 | 11.8 | 12.5921
2022-07-21 | 73 | 660 | 180 | 839.0244 |  | 667.48 | 11.8 | 12.0209
2022-07-22 | 74 | 658 | 180 | 828.5366 |  | 674.36 | 11.8 | 11.5068
2022-07-25 | 75 | 656 | 180 | 818.0488 |  | 681.24 | 11.8 | 11.0441
2022-07-26 | 76 | 655 | 180 | 805 |  | 688.12 | 11.8 | 10.6277
2022-07-27 | 77 | 651 | 180 | 795 |  | 695 | 11.2 | 10.253
2022-07-28 | 78 | 647 | 180 | 784 |  | 705.175 | 11.2 | 10.2452
2022-08-02 | 79 | 643 | 180 | 774 |  | 715.35 | 11.2 | 10.2381
2022-08-03 | 80 | 641 | 180 | 761 |  | 725.525 | 11.2 | 10.2318
2022-08-04 | 81 | 630 | 180 | 750.4306 |  | 735.7 | 11.2 | 10.2261
2022-08-05 | 82 | 629 | 180 | 739.8611 |  | 744.15 | 11.2 | 10.0485
2022-08-08 | 83 | 618 | 180 | 729.2917 |  | 752.6 | 11.2 | 9.8887
2022-08-09 | 84 | 607 | 180 | 718.7222 |  | 761.05 | 11.2 | 9.7448
2022-08-10 | 85 | 596 | 180 | 708.1528 |  | 769.5 | 11.2 | 9.6153
2022-08-11 | 86 | 587 | 180 | 695 |  | 777.95 | 11.2 | 9.4988
2022-08-12 | 87 | 577 | 180 | 684.9275 |  | 786.4 | 11.2 | 9.3939
2022-08-15 | 88 | 566 | 180 | 674.8551 |  | 788.6667 | 11.2 | 8.6812
2022-08-16 | 89 | 536 | 190 | 661 |  | 790.9333 | 11.2 | 8.0397
2022-08-17 | 90 | 532 | 190 | 650.6719 |  | 800.0222 | 11.2 | 8.1447 | 1900.4117
2022-08-18 | 91 | 528 | 190 | 640.3438 |  | 809.1111 | 11.2 | 8.2391
2022-08-19 | 92 | 524 | 190 | 630.0156 |  | 818.2 | 8.5 | 8.3241
2022-08-22 | 93 | 520 | 190 | 619.6875 |  | 827.2889 | 8.5 | 8.4005
2022-08-23 | 94 | 530 | 210 | 606 |  | 836.3778 | 8.5 | 8.4694
2022-08-24 | 95 | 510 | 210 | 595.7288 |  | 845.4667 | 8.5 | 8.5313
2022-08-25 | 96 | 490 | 210 | 585.4576 |  | 854.5556 | 8.5 | 8.5871
2022-08-26 | 97 | 470 | 210 | 575.1864 |  | 863.6444 | 8.5 | 8.6373
2022-08-29 | 98 | 450 | 210 | 564.9153 |  | 872.7333 | 8.5 | 8.6824
2022-08-30 | 99 | 429 | 210 | 551 |  | 881.8222 | 8.5 | 8.7231
2022-08-31 | 100 | 428 | 210 | 541.1607 |  | 890.9111 | 8.5 | 8.7597
2022-09-01 | 101 | 428 | 210 | 531.3214 |  | 900 | 8.5 | 8.7926
2022-09-06 | 102 | 427 | 210 | 518 |  | 910.3571 | 8.5 | 8.949
2022-09-07 | 103 | 424 | 210 | 508.4074 |  | 920.7143 | 8.5 | 9.0898
2022-09-08 | 104 | 418 | 222 | 540 |  | 931.0714 | 8.5 | 9.2166
2022-09-09 | 105 | 410 | 222 | 531.9412 |  | 941.4286 | 8.5 | 9.3306
2022-09-12 | 106 | 402 | 222 | 523.8824 |  | 951.7857 | 8.5 | 9.4333
2022-09-13 | 107 | 396 | 222 | 515.8235 |  | 962.1429 | 8.5 | 9.5257
2022-09-14 | 108 | 387 | 222 | 507.7647 |  | 972.5 | 8.5 | 9.6088
2022-09-15 | 109 | 378 | 222 | 499.7059 |  | 982.8571 | 8.5 | 9.6836
2022-09-16 | 110 | 369 | 222 | 491.6471 |  | 993.2143 | 8.5 | 9.751
2022-09-19 | 111 | 359 | 222 | 483.5882 |  | 1003.5714 | 9.2 | 9.8116
2022-09-20 | 112 | 338 | 222 | 475.5294 |  | 1013.9286 | 9.2 | 9.8662
2022-09-21 | 113 | 332 | 222 | 467.4706 |  | 1024.2857 | 9.2 | 9.9153
2022-09-22 | 114 | 326 | 222 | 459.4118 |  | 1034.6429 | 9.2 | 9.9595
2022-09-23 | 115 | 318.3661 | 222 | 458.1744 |  | 1045 | 10.1 | 9.9992
2022-09-26 | 116 | 312.7634 | 222 | 442.612 |  | 1055.7464 | 10.1 | 10.0739
2022-09-27 | 117 | 307.1607 | 222 | 427.0496 |  | 1066.4928 | 10.1 | 10.1412
2022-09-28 | 118 | 301.558 | 222 | 411.4872 |  | 1077.2392 | 10.1 | 10.2017
2022-09-29 | 119 | 295.9554 | 222 | 395.9248 |  | 1087.9856 | 10.1 | 10.2562
2022-09-30 | 120 | 290.3527 | 222 | 380.3624 |  | 1098.7319 | 10.1 | 10.3052
2022-10-03 | 121 | 284.75 | 222 | 364.8 | 364.8 | 1109.4783 | 10.1333 | 10.3493
2022-10-04 | 122 |  |  |  | 354.6667 | 1109.4783 | 10.1 | 10.3493
2022-10-05 | 123 |  |  |  | 344.5333 | 1109.4783 | 10.1 | 10.3493
2022-10-06 | 124 |  |  |  | 334.4 | 1109.4783 | 10.1 | 10.3493
2022-10-11 | 125 |  |  |  | 324.2667 | 1109.4783 | 10.1 | 10.3493
2022-10-12 | 126 |  |  |  | 314.1333 | 1109.4783 | 10.1 | 10.3493
2022-10-13 | 127 |  |  |  | 304 | 1109.4783 | 10.1 | 10.3493
2022-10-14 | 128 |  |  |  | 293.8667 | 1109.4783 | 10.1 | 10.3493
2022-10-17 | 129 |  |  |  | 283.7333 | 1109.4783 | 10.1 | 10.3493
2022-10-18 | 130 |  |  |  | 273.6 | 1109.4783 | 10.1 | 10.3493
2022-10-19 | 131 |  |  |  | 263.4667 | 1109.4783 | 10.1 | 10.3493
2022-10-20 | 132 |  |  |  | 253.3333 | 1109.4783 | 10.1 | 10.3493
2022-10-21 | 133 |  |  |  | 243.2 | 1109.4783 | 10.1 | 10.3493
2022-10-24 | 134 |  |  |  | 233.0667 | 1109.4783 | 10.1 | 10.3493
2022-10-25 | 135 |  |  |  | 222.9333 | 1109.4783 | 10.1 | 10.3493
2022-10-26 | 136 |  |  |  | 212.8 | 1109.4783 | 10.1 | 10.3493
2022-10-27 | 137 |  |  |  | 202.6667 | 1109.4783 | 10.1 | 10.3493
2022-10-28 | 138 |  |  |  | 192.5333 | 1109.4783 | 10.1 | 10.3493
2022-10-31 | 139 |  |  |  | 182.4 | 1109.4783 | 10.1 | 10.3493
2022-11-01 | 140 |  |  |  | 172.2667 | 1109.4783 | 10.1 | 10.3493
2022-11-02 | 141 |  |  |  | 162.1333 | 1109.4783 | 10.1 | 10.3493
2022-11-03 | 142 |  |  |  | 152 | 1109.4783 | 10.1 | 10.3493
2022-11-04 | 143 |  |  |  | 141.8667 | 1109.4783 | 10.1 | 10.3493
2022-11-07 | 144 |  |  |  | 131.7333 | 1109.4783 | 10.1 | 10.3493
2022-11-08 | 145 |  |  |  | 121.6 | 1109.4783 | 10.1 | 10.3493
2022-11-09 | 146 |  |  |  | 111.4667 | 1109.4783 | 10.1 | 10.3493
2022-11-10 | 147 |  |  |  | 101.3333 | 1109.4783 | 10.1 | 10.3493
2022-11-11 | 148 |  |  |  | 91.2 | 1109.4783 | 10.1 | 10.3493
2022-11-14 | 149 |  |  |  | 81.0667 | 1109.4783 | 10.1 | 10.3493
2022-11-15 | 150 |  |  |  | 70.9333 | 1109.4783 | 10.1 | 10.3493
2022-11-16 | 151 |  |  |  | 60.8 | 1109.4783 | 10.1 | 10.3493
2022-11-17 | 152 |  |  |  | 50.6667 | 1109.4783 | 10.1 | 10.3493
2022-11-18 | 153 |  |  |  | 40.5333 | 1109.4783 | 10.1 | 10.3493
2022-11-21 | 154 |  |  |  | 30.4 | 1109.4783 | 10.1 | 10.3493
2022-11-22 | 155 |  |  |  | 20.2667 | 1109.4783 | 10.1 | 10.3493
2022-11-23 | 156 |  |  |  | 10.1333 | 1109.4783 | 10.1 | 10.3493
2022-11-24 | 157 |  |  |  | 1.7764e-13 | 1109.4783 | 10.1 | 10.3493

## Globals
Holidays:
2022-04-15 | Good Friday
2022-04-18 | company day
2022-05-23 | Victoria Day
2022-05-27 | company day
2022-07-01 | Canada Day
2022-07-04 | company day
2022-07-29 | company day
2022-08-01 | Civic holiday
2022-09-02 | company day
2022-09-05 | Labour Day
2022-10-07 | company day
2022-10-10 | Thanksgiving Day
2022-12-25 | Christmas Day
2022-12-26 | Boxing Day
2023-01-01 | New Year's Day
2023-02-20 | Family Day
2023-04-07 | Good Friday
2023-04-10 | company day
2023-05-22 | Victoria Day